## Stories
ID | Story | Estimation (hours) | Priority | Sprint When Finished
1 | Display a list of recipes | 9 | 1 | Sprint 1/ Sprint 2
2 | Allow the user to create an account and login | 6 | 1 | Sprint 1/Sprint2
3 | Add recipes to a calendar for meal planning | 6 | 1 | Sprint3
4 | Create shopping list with ingredients from a users selected recipes | 8 | 1 | Sprint3
5 | Allow basic filtering and searching of recipes | 10 | 1 | Sprint1/Sprint 2/Sprint3
6 | Allow user to search for recipes with ingredients and cookware they have | 10 | 1 | Sprint3
7 | Allow user to export shopping list | 8 | 2 | Not Implemented
8 | Calculate average ingredient cost | 6 | 3 | Not Implemented
9 | Provide accesibility options to the user like text to speech and casting | 4 | 3 | Not Implemented
10 | Allow user to upload handwritten recipes | 8 | 3 | Not Implemented
11 | Incorporate a social aspect to the user experience | 16 | 3 | Not Implemented
12 | Create a details page for the recipes and allow addition to favorites | 3 | 1 | Sprint 2
13 | Create favorites page and allow user to add recipes to favorites | 4 | 1 | Sprint1/Sprint2
14 | Create pantry where user's ingredients are stored | 6 | 1 | Sprint1/Sprint3
15 | Create a page where users can perform tasks related to account information | 4 | 1 | Sprint 1/Sprint3

## Tasks
Story Number | Task ID | Task Description | Hours Estimation
1 | a | Create UI for serach page | 4
1 | b | Implement scraping tool | 1
1 | c | Improve the search algorithm results | 3
1 | d | Implement measurement conversions for ingredients | 1
2 | a | UI for login page (connecting to google and facebook) | 1
2 | b | UI for create account | 1
2 | c | UI for view/edit account information/ favorites | 2
2 | d | Backend for User info | 3
2 | e | Connecting backend to frontend UI | 3
3 | a | Calendar to add recipes on certain days | 3
3 | b | Add selector for what weeks/days to aggregate into the shopping list | 1
4 | a | Compile recipes ingredients from selected weeks/days | 2
4 | b | Allow the shopping list to be exported to pdf or printed | 1
5 | a | Add list of filters | 2
5 | b | Scrape relevant information from recipes for filters | 3
5 | c | Implement search function | 5
12 | a | Create UI for details page | 3
12 | b | Add functionality to add to favorites | 3